## Sheet1
Week | Topic | Time effort
Project Plan
23/2021 | Create Spreadsheet | low
23/2021 | Create Trello board | low
Setup Azure Cloud Shell | Project
23/2021 | Create cloud-based development environment (Github) | low
23/2021 | Create project scaffolding (Makefile) | low
23/2021 | Local test of Makefile | low
Configure GitHub Actions | Project
23/2021 | Enable Github Actions | low
23/2021 | Replace YAML code | low
23/2021 | Verify remote tests pass | High
CD on Azure | Project
24/2021 | Replace scaffolding code with provided flask code | low
24/2021 | Authorize Azure App Service | medium
24/2021 | Enable CD with Azure Pipelines | high
24/2021 | Test Azure Pipelines YAML | low
24/2021 | Enable GitHub + Azure Pipelines | high
24/2021 | Deployment of project in Azure Pipelines | medium
24/2021 | Verfiy prediction | low
Documentation | Project
25/2021 | Create README | medium
25/2021 | Create Screencast | medium
Q3/2021 | Submission of project
2021 | Review of project and make sure it still works
23/2021